## Sheet1
Change Request Id | Date Submitted | Submitted By | Description Of Change | Reason/Justification | Impact Analysis (Done by Manager) | Priority | Approval Status | Approved By and Date
1 | 2026-06-12 | Exam Controller | Online Exam Registration Module For Student | Reduce Paper Work, Reduce queues, Donot visit university for registration inperson | Core Module, Need database, login/signup ui,registration form ui | HIGH | Approved | Project Manager 13-June-2026
2 | 2026-06-11 | project Manager | Admin Dashboard ,generate report for student result,download/export in excel format | Admin/Exam Controller need report without any one help | Admin Dashboard, Export/download of Business logic | Medium | Approved | Project Manager 13-June-2026
3 | 2026-06-14 | Student Affairs Officer | SMS & Email Notification Module for Exam Schedule and Results | Students should receive instant updates regarding exams and results | Requires integration with email/SMS services, notification templates, and database modifications | Medium | Approved | Project Manager 15-June-2026
4 | 2026-06-15 | Exam Controller | Online Admit Card Generation and Download Module | Students can download admit cards without visiting the examination office | Requires new UI screens, PDF generation functionality, and database updates | High | Approved | Project Manager 16- June-2026