## Sheet1
StartDate | Inventory Management System | [5 empty] | Calendar Week-18 (2026) | [6 empty] | Calendar Week-19 (2026) | [6 empty] | Calendar Week-20 (2026) | [6 empty] | Calendar Week-21 (2026) | [6 empty] | Calendar Week-22 (2026) | [6 empty] | Calendar Week-23 (2026) | [6 empty] | Calendar Week-24 (2026) | [6 empty] | Calendar Week-25 (2026) | [6 empty] | Calendar Week-26 (2026) | [6 empty] | Calendar Week-27 (2026)
2026-05-01 | [6 empty] | April |  |  |  | May | [6 empty] | May | [6 empty] | May | [6 empty] | May | [6 empty] | May |  |  | June | [6 empty] | June | [6 empty] | June | [6 empty] | June | [6 empty] | June
Serial No | Activity | Duration | Plan Start | Plan End | Responsible | Predecessor | time axis 2026-04-27 to 2026-07-05
|  |  | Actual Start | Actual End | time axis 2026-04-27 to 2026-07-05
1 | Project Planning Phase | 5 | 2026-05-01 | 2026-05-05 | Project Manager | - | bar: 2026-05-01 to 2026-05-05
|  |  | 2026-05-01 | 2026-05-05 | bar: 2026-05-01 to 2026-05-05
1.1 | Project Charter Preparation | 2 | 2026-05-01 | 2026-05-02 | Project Manager | - | bar: 2026-05-01 to 2026-05-02
|  |  | 2026-05-02 | 2026-05-03 | bar: 2026-05-02 to 2026-05-03
1.2 | Scope Definition | 1 | 2026-05-03 | 2026-05-03 | Project Manager | 1.1 | bar: 2026-05-03
|  |  | 2026-05-03 | 2026-05-03 | bar: 2026-05-03
1.3 | Feasibility Study | 2 | 2026-05-04 | 2026-05-05 | Project Manager | 1.2 | bar: 2026-05-04 to 2026-05-05
|  |  | 2026-05-04 | 2026-05-05 | bar: 2026-05-04 to 2026-05-05
2 | Analysis & Design Phase | 9 | 2026-05-06 | 2026-05-14 | Analyst Team | 1 | bar: 2026-05-06 to 2026-05-14
|  |  | 2026-05-06 | 2026-05-14 | bar: 2026-05-06 to 2026-05-14
2.1 | Requirements Gathering | 3 | 2026-05-06 | 2026-05-08 | Analyst Team | 1.3 | bar: 2026-05-06 to 2026-05-08
|  |  | 2026-05-06 | 2026-05-08 | bar: 2026-05-06 to 2026-05-08
2.2 | Database Schema Design | 3 | 2026-05-09 | 2026-05-11 | Database Team | 2.1 | bar: 2026-05-09 to 2026-05-11
|  |  | 2026-05-09 | 2026-05-11 | bar: 2026-05-09 to 2026-05-11
2.3 | B2B/B2C UI Wireframes | 3 | 2026-05-12 | 2026-05-14 | UI/UX Team | 2.2 | bar: 2026-05-12 to 2026-05-14
|  |  | 2026-05-12 | 2026-05-14 | bar: 2026-05-12 to 2026-05-14
3 | Development Phase | 28 | 2026-05-15 | 2026-06-11 | Development Team | 2 | bar: 2026-05-15 to 2026-06-11
|  |  | 2026-05-15 | 2026-06-11 | bar: 2026-05-15 to 2026-06-11
3.1 | Cloud Infrastructure Setup | 2 | 2026-05-15 | 2026-05-16 | DevOps Team | 2.3 | bar: 2026-05-15 to 2026-05-16
|  |  | 2026-05-14 | 2026-05-15 | bar: 2026-05-14 to 2026-05-15
3.2 | Authentication Module | 3 | 2026-05-17 | 2026-05-19 | Development Team | 3.1 | bar: 2026-05-17 to 2026-05-19
|  |  | 2026-05-17 | 2026-05-19 | bar: 2026-05-17 to 2026-05-19
3.3 | Product Management CRUD | 3 | 2026-05-20 | 2026-05-22 | Development Team | 3.2 | bar: 2026-05-20 to 2026-05-22
|  |  | 2026-05-20 | 2026-05-22 | bar: 2026-05-20 to 2026-05-22
3.4 | Supplier Management CRUD | 3 | 2026-05-23 | 2026-05-25 | Development Team | 3.3 | bar: 2026-05-23 to 2026-05-25
|  |  | 2026-05-23 | 2026-05-25 | bar: 2026-05-23 to 2026-05-25
3.5 | B2C Shopping Cart | 2 | 2026-05-26 | 2026-05-27 | Development Team | 3.4 | bar: 2026-05-26 to 2026-05-27
|  |  | 2026-05-26 | 2026-05-27 | bar: 2026-05-26 to 2026-05-27
3.6 | Retail Checkout System | 2 | 2026-05-28 | 2026-05-29 | Development Team | 3.5 | bar: 2026-05-28 to 2026-05-29
|  |  | 2026-05-28 | 2026-05-29 | bar: 2026-05-28 to 2026-05-29
3.7 | B2B Ordering Engine | 3 | 2026-05-30 | 2026-06-01 | Development Team | 3.6 | bar: 2026-05-30 to 2026-06-01
|  |  | 2026-05-30 | 2026-06-01 | bar: 2026-05-30 to 2026-06-01
3.8 | Multi-Tier Pricing Logic | 2 | 2026-06-02 | 2026-06-03 | Development Team | 3.7 | bar: 2026-06-02 to 2026-06-03
|  |  | 2026-06-02 | 2026-06-03 | bar: 2026-06-02 to 2026-06-03
3.9 | Stock Sync Engine | 2 | 2026-06-04 | 2026-06-05 | Development Team | 3.8 | bar: 2026-06-04 to 2026-06-05
|  |  | 2026-06-04 | 2026-06-05 | bar: 2026-06-04 to 2026-06-05
3.1 | Low Stock Monitoring | 1 | 2026-06-06 | 2026-06-06 | Development Team | 3.9 | bar: 2026-06-06
|  |  | 2026-06-06 | 2026-06-06 | bar: 2026-06-06
3.11 | ROP Notifications System | 1 | 2026-06-07 | 2026-06-07 | Development Team | 3.1 | bar: 2026-06-07
|  |  | 2026-06-07 | 2026-06-07 | bar: 2026-06-07
3.12 | PDF/Excel Reporting Module | 4 | 2026-06-08 | 2026-06-11 | Development Team | 3.11 | bar: 2026-06-08 to 2026-06-11
|  |  | 2026-06-08 | 2026-06-11 | bar: 2026-06-08 to 2026-06-11
4 | Testing Phase | 5 | 2026-06-12 | 2026-06-16 | QA Team | 3 | bar: 2026-06-12 to 2026-06-16
|  |  | 2026-06-12 | 2026-06-16 | bar: 2026-06-12 to 2026-06-16
4.1 | Unit & Integration Testing | 3 | 2026-06-12 | 2026-06-14 | QA Team | 3.12 | bar: 2026-06-12 to 2026-06-14
|  |  | 2026-06-12 | 2026-06-14 | bar: 2026-06-12 to 2026-06-14
4.2 | User Acceptance Testing | 2 | 2026-06-15 | 2026-06-16 | QA Team And Stakeholders | 4.1 | bar: 2026-06-15 to 2026-06-16
|  |  | 2026-06-15 | 2026-06-16 | bar: 2026-06-15 to 2026-06-16
5 | Deployment Phase | 3 | 2026-06-17 | 2026-06-19 | Project Manager | 4 | bar: 2026-06-17 to 2026-06-19
|  |  | 2026-06-17 | 2026-06-19 | bar: 2026-06-17 to 2026-06-19
5.1 | Data Migration | 2 | 2026-06-17 | 2026-06-18 | Database Team | 4.2 | bar: 2026-06-17 to 2026-06-18
|  |  | 2026-06-17 | 2026-06-18 | bar: 2026-06-17 to 2026-06-18
5.2 | Final Submission & Review | 1 | 2026-06-19 | 2026-06-19 | Project Manager | 4.3 | bar: 2026-06-19
|  |  | 2026-06-19 | 2026-06-19 | bar: 2026-06-19